## Sheet1
URBAN WASTE SEGGREGATING ROBOTIC ARM USING MACHINE LEARNING
WORK BREAK DOWN STRUCTURE
CHETHANA BM |  |  | ANUSHREE G |  |  | Omkar Amarnath A.S |  |  | Ananth Bharadwaj BC
TASKS | START DATE | END DATE | TASKS | START DATE | END DATE | Tasks | Start Date | End Date | Tasks | Start Date | End Date
Literature survey on waste management | 2019-09-26 | 2019-09-28 | Literature survey on Image Processing | 2019-09-26 | 2019-09-28 | Literature Survey on Urban Waste | 2019-09-29 | 2019-10-03 | Literature Survey on Urban Waste | 2019-09-29 | 2019-10-03
Literature survey on image classification | 2019-09-26 | 2019-09-28 | Literature survey on Supervised and Unsupervised algorithms | 2019-09-29 | 2019-09-30 | Literature Survey on Robotic Arm | 2019-10-04 | 2019-10-12 | Literature Survey on Robotic Arm | 2019-10-04 | 2019-10-12
Literature survey on machine learning algorithms | 2019-09-27 | 2019-09-28 | Started with the System Requirement Specifications | 2019-10-01 | 2019-10-10 | Collected the required Components for the assemble of the Arm | 2019-10-13 | 2019-10-15 | Collected the required Components for the assemble of the Arm | 2019-10-13 | 2019-10-15
Literature survey on GAN | 2019-09-28 | 2019-09-29 | Understanding about Opencv | 2019-10-11 | 2019-10-13 | Literature Survey on the assembly of the Arm. | 2019-10-16 | 2019-10-19 | Literature Survey on the assembly of the Arm. | 2019-10-16 | 2019-10-19
Understanding discriminator and generator | 2019-09-29 | 2019-09-29 | Worked on KRISE Challenge Proposal | 2019-10-14 | 2019-10-18 | Started with the Assembly of the Arm | 2019-10-20 | 2019-10-25 | Started with the Assembly of the Arm | 2019-10-20 | 2019-10-25
Looked through other classification algorithms | 2019-09-30 | 2019-10-02 | Installed Python,PIP and Open CV | 2019-10-19 | 2019-10-22 | Started with the Assembly of the Arm | 2019-10-26 | 2019-10-30 | Started with the Assembly of the Arm | 2019-10-26 | 2019-10-30
Literature survey on CNN | 2019-10-03 | 2019-10-05 | Collected about 1k images of Dry waste | 2019-10-23 | 2019-10-25 | Programmed the Arm to do the required movements | 2019-10-31 | 2019-11-03 | Programmed the Arm to do the required movements | 2019-10-31 | 2019-11-03
Trying a small snippet on CNN | 2019-10-06 | 2019-10-07 | Collected around 1.5k images of Dry waste | 2019-10-26 | 2019-10-28 | Final exmas and vacation | 2019-11-04 | 2020-01-31 | Final exams and vacation | 2019-11-04 | 2020-01-31
Looking through how to work on it | 2019-10-08 | 2019-10-10 | Collected 20 images of Wet waste | 2019-10-29 | 2019-10-30 | Research on the design of the bot | 2020-02-01 | 2020-02-10 | Research on the design of the arm | 2020-02-01 | 2020-02-10
Literature survey on tensorflow | 2019-10-11 | 2019-10-13 | Was able to convert one image at a time from dataset to GrayScale | 2019-10-31 | 2019-11-01 | Designing a new and a bigger bot | 2020-02-11 | 2020-02-25 | Designing a new robotic arm | 2020-02-11 | 2020-02-25
Trying to import tensorflow and tensorflow installation | 2019-10-14 | 2019-10-17 | Worked on the Power Point Presentation | 2019-11-02 | 2019-11-03 | Working on the assembly of new bot | 2020-02-26 | 2020-03-03 | Working on the assembly of new arm | 2020-02-26 | 2020-03-03
Installing anaconda navigator | 2019-10-18 | 2019-10-19 | Final exams and vacation | 2019-11-04 | 2020-01-31 | Trying with DC motors | 2020-03-04 | 2020-03-16 | 3D printing a new robotic arm | 2020-03-04 | 2020-03-16
Working on tensorflow | 2019-10-20 | 2019-10-20 | Collecting dataset | 2020-01-01 | 2020-01-15 | Working on the control of the bot using bluetooth module | 2020-03-17 | 2020-04-05 | Working on the control of the arm | 2020-03-17 | 2020-04-05
Learning how to load dataset | 2019-10-21 | 2019-10-23 | Labelling fruit waste using labelimg | 2020-01-16 | 2020-01-21 | Trying the opposite of line following | 2020-04-06 | 2020-04-17 | Working on the pick and place movement of the arm | 2020-04-06 | 2020-04-17
Trying to preprocess an image | 2019-10-24 | 2019-10-24 | Labelling leaf waste using labelimg | 2020-01-22 | 2020-01-27 | Testing the movement of the bot | 2020-04-18 | 2020-04-29 | Testing the complete movement of the arm with new motors | 2020-04-18 | 2020-04-29
Building the model,compiling it, evaluationg accuracy | 2019-10-25 | 2019-10-27 | Labelling paper waste using labelimg | 2020-01-28 | 2020-02-07 | Working on the serial connection between the pi and arduino | 2020-04-30 | 2020-05-07 | working on the serial connection between the pi and arduino | 2020-04-30 | 2020-05-07
Predicting the model | 2019-10-28 | 2019-10-29 | Working on the report | 2020-02-08 | 2020-02-18 | Working on the entire assembly of the arm and the bot | 2020-05-08 | 2020-05-16 | Working on the entire assembly of the arm and the bot | 2020-05-08 | 2020-05-16
studying for internals | 2019-10-29 | 2019-10-31 | Re-collection of dataset | 2020-02-19 | 2020-02-27 | Testing the entire assembly of the arm and the bot | 2020-05-17 | 2020-05-25 | Testing the entire assembly of the arm and the bot | 2020-05-17 | 2020-05-25
collecting the dataset | 2019-11-01 | 2019-11-03 | Renaming of all images | 2020-02-28 | 2020-03-05 | Stitching of the entire system | 2020-05-26 | 2020-06-04 | Stitching of the entire system | 2020-05-26 | 2020-06-04
Final exmas and vacation | 2019-11-04 | 2020-01-31 | Labelling of all the images | 2020-03-06 | 2020-03-13 | Testing the system | 2020-06-05 | 2020-06-06 | Testing of the system | 2020-06-05 | 2020-06-06
Literature survey on Object detection using tensorflow API | 2020-02-01 | 2020-02-04 | Working on the report | 2020-03-14 | 2020-03-27 | Working on fine tuning of the model | 2020-06-06 | 2020-06-10 | Working on fine tuning of the model | 2020-06-06 | 2020-06-10
Research on SSD and Faster-RCNN | 2020-02-05 | 2020-02-08 | Research on SCP protocol | 2020-03-28 | 2020-04-05 | Working on the report | 2020-06-11 | 2020-06-25 | Working on the report | 2020-06-11 | 2020-06-25
Trying out GPU | 2020-02-09 | 2020-02-11 | Trying clicking of an image using pi | 2020-04-06 | 2020-04-14
Understanding Google colab | 2020-02-12 | 2020-02-13 | Trying to send an image from pi to end system using SCP | 2020-04-15 | 2020-04-28
Trying object detection for paper class label | 2020-02-14 | 2020-02-24 | Research on MQTT protocol | 2020-04-29 | 2020-05-03
Collection of 3 data class labels | 2020-02-25 | 2020-03-02 | Setting up the client and server using SSH protocol | 2020-05-04 | 2020-05-07
Labelling of total 1500 images | 2020-03-03 | 2020-03-07 | Trying to send "hi" from pi to end sysytem | 2020-05-08 | 2020-05-12
Splitting train and test images | 2020-03-08 | 2020-03-09 | Testing MQTT between pi and end system | 2020-05-13 | 2020-05-17
Converting all xml files into csv test and train files | 2020-03-10 | 2020-03-13 | Setting up publisher on pi to click an image using MQTT | 2020-05-18 | 2020-05-21
Converting csv files into tf record files | 2020-03-14 | 2020-03-20 | Setting up subscriber on the end system using MQTT | 2020-05-22 | 2020-05-25
Downloading the ssd model | 2020-03-21 | 2020-03-23 | Stitching the entire system using MQTT | 2020-05-26 | 2020-06-04
Making changes to ssd model | 2020-03-24 | 2020-04-02 | Testing the entire sysytem | 2020-06-05 | 2020-06-06
Training of the model | 2020-04-03 | 2020-04-15 | Working on the fine tuning of the system | 2020-06-07 | 2020-06-10
Checking performance | 2020-04-16 | 2020-04-20 | Working on the report | 2020-06-11 | 2020-06-25
Changing of few images in dataset | 2020-04-21 | 2020-04-24
Repeatig the entire process | 2020-04-25 | 2020-05-04
Re-training the model | 2020-05-05 | 2020-05-12
Testing the model for live data | 2020-05-13 | 2020-05-15
Trying to run the algorithm for an image | 2020-05-16 | 2020-05-18
Extracting the class name | 2020-05-19 | 2020-05-20
Extracting the coordinates | 2020-05-21 | 2020-05-23
Extracting the confidence scores | 2020-05-24 | 2020-05-26
Stitching the model using MQTT | 2020-05-27 | 2020-06-04
Testing the final sysytem | 2020-06-05 | 2020-06-06
Working on fine tuning of the model | 2020-06-07 | 2020-06-10
Working on the report | 2020-06-11 | 2020-06-25